## Action Plan
Union Of Kingston Students - Ongoing Sustainability Action Plan - Updated 27/04/2018
Goal / Action stages | Desired Outcome | Staff Member/Department Responsible | Date to Begin | Date Due | % Complete
Goal 1 | Reduce Waste at Fresher's Fayre 2017 | Student Union
Action stage 1 | 10% Reduction in Students Union printed materials | Alastair Burr - SA Manager / Mar Coms Manager | 2017-08-01 | 2018-08-18 | 100%
Action stage 2 | 0% Single Use Plastic Items / Bags at Fresher's Fayre | Alastair Burr - SA Manager / Mar Coms Manager | 2017-08-01 | 2018-09-18 | 100%
Action stage 3 | All printed publicity published on Union Website | Alastair Burr - SA Manager / Mar Coms Manager | 2017-08-01 | 2018-09-18 | 100%
Goal 2 | Submit Opportunities Funding Request For Sustainability Project Assistant (Student Staff)
Action stage 1 | Draft Opportunities Bid - Co-written by the Sustainability Hub | Alastair Burr - SA Manager / KU Sus Hub | 2017-11-01 | 2018-01-05 | 0%
Action stage 2 | Submit Opportunities Funding bid For Sustainability Assistant | Alastair Burr - SA Manager / KU Sus Hub | 2017-11-01 | 2018-01-05 | 0%
Action stage 3 | Advertise role to students | Alastair Burr - SA Manager / KU Sus Hub | 2017-11-01 | 2018-01-05 | 0%
Action stage 4 | Hire and train Sustainability Project Assistant | Alastair Burr - SA Manager / KU Sus Hub | 2017-11-01 | 2018-01-05 | 0%
Goal 3 | Green Impact Submission to NUS
Action stage 1 | Identify gaps in Student' Union operations in line with Green Impact criteria | Alastair Burr / Safrina Ahmed/ KU Sus Hub | 2018-01-09 | 2018-05-05 | 100%
Action stage 2 | Meet with Kingston University Estates (Energy) to create an energy assessment for the Union office/ social space | Alastair Burr - SA Manager | 2017-02-17 | 2017-02-17 | 100%
Action stage 3 | Publish energy assessment on Students' Union Website | Alastair Burr | 2018-02-27 | 2018-02-27 | 100%
Action stage 4 | Cycling Mileage rates review in line with Government for Union / Student Staff | Safrina Ahmed / Alastair Burr | 2018-02-02 | 2018-02-02 | 100%
Action stage 7 | Fairtrade Fortnight Events with Elior | Safrina Ahmed / Green Connectors | 2018-02-26 | 2018-03-11 | 100%
Action stage 8 | Review all Students' Union clothing contracts to be inline with Fairtrade - Tender process | Alastair Burr - SA Manager / Mar Coms Manager | 2018-02-22 | 2018-04-23 | 100%
Action stage 9 | Submit Green Impact Workbook | Safrina Ahmed / Alastair Burr / KU Sus Hub | 2018-04-24 | 2018-04-27 | 100%
Action stage 10 | Environmental Impact - Aspects and Impacts Register - Create and Publish | Alastair Burr - SA Manager / KU Sus Hub | 2018-01-23 | 2018-04-23 | 75%
Goal 4 | Campaign / Influencing - Varsity
Action stage 1 | Develop campaign brief - To show the link between sports, health and sustainability | Alastair Burr - SA Manager / KU Sus Hub | 2018-01-01 | 2018-02-01 | 100%
Action stage 2 | Identify different sustainability projects / initiatives to include as part of Varsity 2018 | Alastair Burr - SA Manager / KU Sus Hub | 2018-01-01 | 2018-02-01 | 100%
Action stage 3 | Present campaign proposal to City University, and Kingston Sports Department | Alastair Burr - SA Manager / KU Sus Hub | 2018-02-01 | 2018-03-01 | 100%
Action stage 4 | Book and facilitate sustainability intiatives for Varsity 2018 | Alastair Burr - SA Manager / KU Sus Hub | 2018-02-01 | 2018-03-01 | 100%
Action stage 5 | Confirm with all intiatives, and develop impact recording framework | Alastair Burr - SA Manager / KU Sus Hub | 2018-02-01 | 2018-03-01 | 100%
Action stage 4 | Tv Screens, and Poster to advertise the event | Alastair Burr - SA Manager / KU Sus Hub | 2018-03-10 | 2018-03-10 | 100%
Action stage 5 | Launch campaign | Alastair Burr - SA Manager / KU Sus Hub | 2018-03-21 | 2018-03-21 | 100%
Goal 5 | Halls Re-Use Project
Action stage 1 | Meet with Sustainability Operations Sustainability Manager, Sustainability Hub | Alastair Burr - SA Manager | 2017-05-03 | 2017-05-03 | 100%
Action stage 2 | Meet with Student Participation Officer, Student Engagement & Enhancement | Alastair Burr - SA Manager | 2017-05-03 | 2017-05-03 | 100%
Action stage 3 | Recruit Halls Connects and Student Volunteers for Halls Re-Use | Alastair Burr / Ryan Jones / Richard Anderson | 2017-05-04 | 2017-05-19 | 100%
Action stage 4 | Train and place students at halls for Re-Use days | Alastair Burr / Ryan Jones / Richard Anderson | 2017-05-24 | 2017-06-30 | 100%
Action stage 4 | Record all waste collected, and produe report on the success of the project | Alastair Burr / Ryan Jones / Richard Anderson | 2017-06-20 | 2017-07-19 | 100%
Goal 6 | Fresher's Fayre 2017
Action stage 1 | Create new marketing rates for stall holders that can show reduced waste / sustainability within their stall | Alastair Burr - SA Manager / Marketing Dept | 2017-07-12 | 2018-07-15 | 100%
Action stage 2 | Create fines structure for stall holders for excessive waste on day | Alastair Burr - SA Manager | 2017-07-19 | 2017-07-19 | 100%
Action stage 3 | Educate Sports & Societies at committee training days on how to run sustainable fresher's fayre stall | Alastair Burr - SA Manager | 2017-07-01 | 2017-07-01 | 100%
Action stage 4 | Educate Union/ University departments on how to run a sustainable fresher's fayre stall | Alastair Burr - SA Manager | 2017-07-01 | 2017-07-01 | 100%
Action stage 5 | Freshers Fayre 2018 improve on metrixs and sustainability / Plastic Free | Alastair Burr - SA Manager | 2018-03-01 | 2018-11-01 | 0%
Goal 7 | Students' Union Goverance
Action stage 1 | Provide training from all motion proposers for AGM / EGM | Alastair Burr - SA Manager / Representation and Democracy Manager | 2018-01-01 | 2018-02-01 | 100%
Action stage 2 | Review all active motions on Union website, and create 'Policy Working Group' to mointor policy progress | Alastair Burr - SA Manager / Representation and Democracy Manager | 2018-03-01 | 2018-03-10 | 100%
Action stage 3 | Review 'Code of Practice' with the University, and include reference to sustainability and parternship working | Alastair Burr - SA Manager | 2018-04-01 | 2018-04-01 | 100%
Action stage 4 | Include Sustainability as part of Part Time, and Full Time officer induction | Alastair Burr - SA Manager / Representation and Democracy Manager | 2018-04-01 | 2018-05-01 | 75%
Goal 8 | Ethical Volunteering Working Group
Action stage 1 | Review the effectiveness of the current Sustainability Working Group | Alastair Burr - SA Manager / Representation and Democracy Manager | 2018-03-01 | 2018-04-01 | 100%
Action stage 2 | Provide feedback on Student Council structure, in reference to EVWG structure | Alastair Burr - SA Manager | 2018-03-01 | 2018-04-01 | 100%
Action stage 3 | Create new terms of reference for Ethical Volunteering Working Group | Alastair Burr - SA Manager | 2018-03-01 | 2018-04-01 | 100%
Action stage 4 | Recruitment plan for EVWG create for the next academic year | Alastair Burr - SA Manager | 2018-03-01 | 2018-04-01 | 50%
Goal 9 | Stationary Amnesty - Re-Use -
Action stage 1 | Stationary Amnesty - Re-Use - Locate University departments with excessive stationary | Safrina Ahmed | 2017-12-11 | 2017-12-16 | 100%
Action stage 2 | Collect Stationary - Place in Union social space for students | Safrina / Office Administrator | 2018-01-15 | 2018-01-19 | 100%
Goal 10 | Campaign - Keep Warm - Refugees Coat Collection
Action stage 1 | Develop campaign brief - Select Charity to work with, and highlight collection points | Alastair Burr - SA Manager / Volunteering Department / Student Proposer | 2018-01-01 | 2018-02-01 | 100%
Action stage 2 | Create marketing campaign to go alongside coat collection points | Alastair Burr - SA Manager / Volunteering Department / Student Proposer | 2018-01-01 | 2018-02-01 | 100%
Action stage 3 | Contact KU Sus Hub and Grundon in reagrds to coat collection point - wheelie bins. | Alastair Burr - SA Manager / Volunteering Department / Student Proposer | 2018-02-01 | 2018-03-01 | 100%
Action stage 4 | Book and facilitates and storage area's for coat collection | Alastair Burr - SA Manager / Volunteering Department / Student Proposer | 2018-02-01 | 2018-03-01 | 100%
Action stage 5 | Message for tags to refugees afternoon at KH, and PR | Alastair Burr - SA Manager / Volunteering Department / Student Proposer | 2018-02-01 | 2018-03-01 | 100%
Action stage 4 | Weight and box up coat collection | Alastair Burr - SA Manager / Volunteering Department / Student Proposer | 2018-03-10 | 2018-03-10 | 100%
Action stage 5 | Report on impact | Alastair Burr - SA Manager / Volunteering Department / Student Proposer | 2018-03-21 | 2018-03-21 | 100%
Action stage 1 | Send items to choosen charity | Alastair Burr - SA Manager / Volunteering Department / Student Proposer | 2018-03-01 | 2018-03-01 | 100%
Goal 11 | Campaign - BCAT
Action stage 1 | Design and Launch BCAT Campaign | Alastair Burr - SA Manager / KU Sus Hub / Student Officers | 01/09/207 | 2022-05-01 | 20%